## Sheet1
4-Wheel Drive Used Car Dealership
4-Wheel Drive
Project Manager: |  | Alyssa Wilcox (AW)
Assistant Project Manager: |  | Wen Zhang (WZ)
Software Engineer: |  | Jorge Valencia (JV)
Software Engineer: |  | Lingyun Yang (LY)
Software Engineer: |  | Taige Huang (TH)
Software Engineer: |  | Cong Ding (CD)
Software Engineer: |  | Chao Zhang (CZ)
| Project Start: | 2020-08-28
[6 empty] | 2020-11-16 |  |  |  | 2020-11-23
|  |  |  | 8 | 15 | 16 | 17 | 18 | 22 | 23 | 27 | 28 | 29 | 30
TASK | ASSIGNED TO | START | END | S | S | M | T | W | S | M | F | S | S | M
Search Bar | bar: START to END
Keyword search results | JV | START: 2020-11-08; END: 2020-11-22
Display keyword search results | JV | START: 2020-11-22; END: 2020-11-22
Modify Vehicle | bar: START to END
Display vehicle data to the form | TH and CZ | START: 2020-11-15; END: 2020-11-17
Save new data to the document | TH and CZ | START: 2020-11-15; END: 2020-11-17
My Favorites | bar: START to END
Add vehicle to My Favorites | LY and WZ | START: 2020-11-15; END: 2020-11-16
Display vehicle to My Favorites | LY and WZ | START: 2020-11-17; END: 2020-11-18
Remove vehicle | LY and WZ | START: 2020-11-18; END: 2020-11-18
My Favorites in the Vehicle | LY and WZ | START: 2020-11-22; END: 2020-11-22
Delete Vehicle | bar: START to END
Delete from vehicle collection | TH and CZ | START: 2020-11-17; END: 2020-11-18
Delete vehicle picture | TH and CZ | START: 2020-11-17; END: 2020-11-18
Filter | bar: START to END
Filter Full Inventory | JV | START: 2020-11-23; END: 2020-11-27
Display Filter Full Inventory | JV | START: 2020-11-23; END: 2020-11-27
Filter Search Results | JV | START: 2020-11-28; END: 2020-11-29
Display Filter Search Results | JV | START: 2020-11-28; END: 2020-11-29
Reset Search Results | JV | START: 2020-11-30; END: 2020-11-30
Special Deals | bar: START to END
Save Vehicle as Special Deal | AW | START: 2020-11-17; END: 2020-11-18
Remove Vehicle as Special Deal | AW | START: 2020-11-17; END: 2020-11-18
Display Special Deals | AW | START: 2020-11-17; END: 2020-11-18