## Sheet1
4-Wheel Drive Used Car Dealership
4-Wheel Drive
Project Manager: |  | Alyssa Wilcox (AW)
Assistant Project Manager: |  | Wen Zhang (WZ)
Software Engineer: |  | Jorge Valencia (JV)
Software Engineer: |  | Lingyun Yang (LY)
Software Engineer: |  | Taige Huang (TH)
Software Engineer: |  | Cong Ding (CD)
Software Engineer: |  | Chao Zhang (CZ)
| Project Start: | 2020-08-28
|  |  |  | September |  |  | October | [13 empty] | November
|  |  |  | 24 | 25 | 28 | 1 | 2 | 3 | 4 | 5 | 9 | 10 | 11 | 12 | 20 | 21 | 22 | 25 | 26 | 2 | 3 | 6 | 7 | 8 | 9 | 10 | 11
TASK | ASSIGNED TO | START | END | T | F | M | T | F | S | S | M | F | S | S | M | T | W | T | S | M | M | T | F | S | S | M | T | W
Login | bar: START to END
Create User Account | LY & WZ | START: 2020-09-24; END: 2020-09-25
Login an Existing User | LY & WZ | START: 2020-09-28; END: 2020-09-28
Create a User Collection in DB | LY & WZ | START: 2020-10-01; END: 2020-10-01
Distinguish Users | LY & WZ | START: 2020-10-01; END: 2020-10-02
Reset Password | LY & WZ | START: 2020-10-03; END: 2020-10-03
Add Vehicle | bar: START to END
Add vehicle data & pic in DB | TH & CZ | START: 2020-10-01; END: 2020-10-01
Modifications to DB structure | TH & CZ | START: 2020-10-03; END: 2020-10-06
Add unique ID to vehicle in DB | TH & CZ | START: 2020-10-09; END: 2020-10-10
Add reference to pic | TH & CZ | START: 2020-10-11; END: 2020-10-12
Error H&ling | AW | START: 2020-11-07; END: 2020-11-08
Display Vehicle | bar: START to END
Read data from database | CD | START: 2020-10-20; END: 2020-11-03
Display title & picture | CD | START: 2020-10-20; END: 2020-11-03
Display vehicle table | CD | START: 2020-10-20; END: 2020-11-03
Display vehicle details | CD | START: 2020-11-03; END: 2020-11-11
UI | bar: START to END; November 7 S to November 11 W
View Inventory UI | AW | START: 2020-10-20; END: 2020-11-03
Car Details UI | AW | START: 2020-10-20; END: 2020-10-26
Homepage UI Updates | AW | START: 2020-11-09; END: 2020-11-09
Search Bar | bar: START to END
Search Inventory | JV | START: 2020-11-08